## Earned Value Management
EARNED VALUE MANAGEMENT SHEET
PROJECT TITLE | DataHarbor Intelligence |  |  |  | PREPARED BY | Bisma Khan |  |  | DATE OF REPORT | 2023-12-01
PLANNED VALUE – WBS IDs and Task Titles listed here will automatically populate on worksheet tabs.
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | GUI Development | 1740 | 420 | 500 | 400 | 50 | 10 | 10 | 10 | 10 | 15 | 100 | 105 | 110
1.2 | Data Integration | 1000 | 350 | 80 | 30 | 40 | 35 | 45 | 100 | 10 | 10 | 100 | 100 | 100
1.3 | Algorithim Implementation | 1180 | 510 | 150 | 75 | 10 | 10 | 15 | 30 | 10 | 20 | 150 | 90 | 110
1.4 | Testing | 1010 | 320 | 150 | 15 | 10 | 15 | 15 | 25 | 15 | 15 | 105 | 150 | 175
2.1 | Documentation | 810 | 210 | 215 | 35 | 20 | 15 | 15 | 10 | 10 | 20 | 100 | 50 | 110
2.2 | User Interface Refinement | 905 | 235 | 130 | 45 | 25 | 55 | 15 | 15 | 15 | 15 | 150 | 85 | 120
2.3 | API Integration | 850 | 320 | 75 | 45 | 30 | 30 | 20 | 15 | 20 | 15 | 100 | 80 | 100
2.4 | Performance Optimization | 926 | 256 | 215 | 110 | 15 | 30 | 15 | 30 | 10 | 10 | 75 | 70 | 90
2.5 | Security Implementation | 850 | 115 | 210 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 105 | 15 | 300
3.1 | User Acceptance Testing | 1220 | 250 | 20 | 15 | 5 | 10 | 15 | 15 | 10 | 5 | 300 | 425 | 150
3.2 | Integration Testing | 870 | 150 | 15 | 10 | 30 | 15 | 15 | 10 | 15 | 15 | 200 | 270 | 125
TBC | TOTAL BUDGETED COST | 11361 | 3136 | 1760 | 795 | 250 | 240 | 195 | 275 | 140 | 155 | 1485 | 1440 | 1490
PV | CUMLATIVE PLANNED VALUE |  | 3136 | 4896 | 5691 | 5941 | 6181 | 6376 | 6651 | 6791 | 6946 | 8431 | 9871 | 11361
ACTUAL COST
AC | CUMULATIVE ACTUAL COST |  | 2609 | 4546 | 5435 | 6050 | 6406 | 6761 | 7230 | 7555 | 7925 | 8314 | 9156 | 10021
EARNED VALUE
EV | CUMULATIVE EARNED VALUE |  | 7700 | 8665 | 7105 | 2235 | 1460 | 1460 | 1460 | 1460 | 1460 | 6355 | 10250 | 14600
PROJECT PERFORMANCE METRICS
CV | COST VARIANCE | ( EV – AC ) | 5091 | 4119 | 1670 | -3815 | -4946 | -5301 | -5770 | -6095 | -6465 | -1959 | 1094 | 4579
SV | SCHEDULE VARIANCE | ( EV – PV ) | 4564 | 3769 | 1414 | -3706 | -4721 | -4916 | -5191 | -5331 | -5486 | -2076 | 379 | 3239
CPI | COST PERFORMANCE INDEX | ( EV / AC ) | 2.9513 | 1.9061 | 1.3073 | 0.36942 | 0.22791 | 0.21594 | 0.20194 | 0.19325 | 0.18423 | 0.76437 | 1.1195 | 1.4569
SPI | SCHEDULE PERFORMANCE INDEX | ( EV / PV ) | 2.4554 | 1.7698 | 1.2485 | 0.3762 | 0.23621 | 0.22898 | 0.21952 | 0.21499 | 0.21019 | 0.75377 | 1.0384 | 1.2851
EAC | ESTIMATED COST AT COMPLETION |  | 3849.4609 | 5960.4277 | 8690.6453 | 30753.4899 | 49848.3329 | 52610.7678 | 56260.2945 | 58789.2842 | 61668.4418 | 14863.1556 | 10148.4211 | 7797.848

## Actual Cost Worksheet
EARNED VALUE MANAGEMENT SHEET
PROJECT TITLE | DataHarbor Intelligence |  |  |  | PREPARED BY | Bisma Khan |  |  | DATE OF REPORT | 2023-12-01
ACTUAL COST – Enter amount of actual costs incurred for each task per period.
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | GUI Development | 1177 | 412 | 300 | 220 | 100 | 10 | 10 | 10 | 70 | 10 | 10 | 10 | 15
1.2 | Data Integration | 1345 | 815 | 220 | 60 | 40 | 15 | 0 | 35 | 55 | 50 | 20 | 30 | 5
1.3 | Algorithim Implementation | 810 | 155 | 180 | 175 | 120 | 3 | 17 | 0 | 35 | 30 | 25 | 55 | 15
1.4 | Testing | 850 | 150 | 105 | 10 |  | 17 | 15 | 85 | 10 | 10 | 110 | 193 | 145
2.1 | Documentation | 688 | 100 | 200 | 15 | 30 | 73 | 78 | 45 | 22 | 43 | 25 | 22 | 35
2.2 | User Interface Refinement | 1258 | 170 | 512 | 22 | 85 | 72 | 82 | 115 | 78 | 55 | 17 | 35 | 15
2.3 | API Integration | 672 | 180 | 135 | 72 | 85 | 10 | 52 | 20 | 7 | 22 | 12 | 72 | 5
2.4 | Performance Optimization | 1050 | 202 | 115 | 190 | 82 | 51 | 70 | 122 | 13 | 110 | 30 | 15 | 50
2.5 | Security Implementation | 765 | 275 | 125 | 100 | 50 | 75 | 10 | 15 | 15 | 20 | 25 | 45 | 10
3.1 | User Acceptance Testing | 714 | 55 | 10 | 10 | 13 | 15 | 11 | 10 | 10 | 10 | 45 | 175 | 350
3.2 | Integration Testing | 692 | 95 | 35 | 15 | 10 | 15 | 10 | 12 | 10 | 10 | 70 | 190 | 220
AC | ACTUAL COST | 10021 | 2609 | 1937 | 889 | 615 | 356 | 355 | 469 | 325 | 370 | 389 | 842 | 865
| CUMULATIVE ACTUAL COST |  | 2609 | 4546 | 5435 | 6050 | 6406 | 6761 | 7230 | 7555 | 7925 | 8314 | 9156 | 10021

## Earned Value Worksheet
EARNED VALUE MANAGEMENT SHEET
PROJECT TITLE | DataHarbor Intelligence |  |  |  | PREPARED BY | Bisma Khan |  |  | DATE OF REPORT | 2023-12-01
CUMULATIVE EARNED VALUE – For each Task per Period, the Percentage Complete is Shown.
WORK BRKDWN STRUCTURE | TASK TITLE | TOTAL BUDGETED COST | PERIOD
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1.1 | GUI Development | 3000 | 60% | 70% | 100% | 40% | 10% | 10% | 10% | 10% | 10% | 30% | 75% | 100%
1.2 | Data Integration | 2500 | 40% | 100% | 30% | 5% | 10% | 10% | 10% | 10% | 10% | 20% | 75% | 100%
1.3 | Algorithim Implementation | 1500 | 75% | 75% | 60% | 10% | 10% | 10% | 10% | 10% | 10% | 35% | 70% | 100%
1.4 | Testing | 1000 | 20% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 80% | 95% | 100%
2.1 | Documentation | 1200 | 70% | 50% | 40% | 10% | 10% | 10% | 10% | 10% | 10% | 45% | 60% | 100%
2.2 | User Interface Refinement | 1500 | 65% | 65% | 45% | 10% | 10% | 10% | 10% | 10% | 10% | 65% | 65% | 100%
2.3 | API Integration | 800 | 75% | 45% | 50% | 10% | 10% | 10% | 10% | 10% | 10% | 30% | 50% | 100%
2.4 | Performance Optimization | 700 | 65% | 35% | 65% | 10% | 10% | 10% | 10% | 10% | 10% | 45% | 45% | 100%
2.5 | Security Implementation | 900 | 75% | 70% | 35% | 10% | 10% | 10% | 10% | 10% | 10% | 40% | 60% | 100%
3.1 | User Acceptance Testing | 1000 | 2% | 2% | 2% | 10% | 10% | 10% | 10% | 10% | 10% | 80% | 80% | 100%
3.2 | Integration Testing | 500 | 2% | 2% | 2% | 10% | 10% | 10% | 10% | 10% | 10% | 80% | 75% | 100%
EV | CUMULATIVE EARNED VALUE |  | 7700 | 8665 | 7105 | 2235 | 1460 | 1460 | 1460 | 1460 | 1460 | 6355 | 10250 | 14600